## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
As the Great Ocean Road Coast and Parks Authority had only been extablished as an Authority for approximatley 1.5 years the Authority had no gender impact assessment conducted for the 2022-2023 period. This will be adressed for the next reporting period.
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Introduce a performance management system | In progress | This strategy was initiated in early 2022 based on the successful procurement of a human Resource Information System (HRIS) with a goal to have implemented by July 2023. For the period July 2022-June 2023 the performance management system was midway through the system build with testing in the later half of 2023 scheduled for implementation late 2023. The system was initially delayed due to the organisation finalising our strategic goals and educating leaders and staff on how their annual performance plans would align to achieve our strategic goas and values organisation behaviours. | Although implementation was planned for June 2023 rescheduling implementation was delayed until October 2023. Management and staff received several communications informing them of the new performance management system particularly its alignment to the organisations 5 year staretgic plan, organisation values and employee development plans. Cuurent takeup of the performance management system for 2022-2023 was approximatley 30% based on manual data collected. We anticipate that this figure will increase in the next reporting period in addition to including intersectional data that will be incorprated in to the new system. | 2023 | People & Culture Manager | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1 to Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Collect recruitment demographic data (beyond gender) in a pilot study | Not started | A pilot study for this action has yet to be established due to available resourcing workload and systems/accurate data capture. Prior to June 2022 the Authority had been collecting data manually from an outdated payroll system. Since the Authority's establishment in December 2020 the collection of recruitment demographic data was collected on an adhoc basis and recorded into excel sprreadsheets and mainly used for annual reporting for the Authority's Board and Annual report. | During the 2022/2023 reporting period the Authority had no system in place to caputre recruitment demographic data. Amongst other gaps in HR's ability to capture, analyse and report on various data, the Authority sought approval with an agreed business case to procure a human Respource Information (including a recruitment module) and Payroll system. Improvement is in progress and with a system implementation scheduled for November 2023 will have the ability to capture demographic data on our recruitment beyond gender. This will enable the organisation to better measure our recruitment efforts and effectiveness of talent attraction strategies. | 2023 | Human Resources Coordinator | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1 to Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 2; Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5; Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Conduct an inclusivity and accessibility audit on the organisation with respect to disability | Not started | This strategy had not yet started for the 2022-2023 reporting period due to change in resource budgeting and workload impacts. Although important has yet to commence due to lack of accessible funds and access to internal resourcing availability. | This audit although not yet started will provide valuable data in understanding our workforce and associated gaps with inclusivity andaccessibility regarding disability. This audit has been rescheduled to be delivered in mid 2024. | 2022 | Human Resources Coordinator | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1; Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Develop specic sourcing strategies to access broader and more diverse talent pools | Ongoing | Developing sourcing strategies to access broader and diverse talent pools is an ongoing effort when sourcing talent. The Authority's network is constantly expanding from identifying recruitment agencies universities and industry specific organisations. This also extends to organisations with a focus on LGBTIQA+, disabilities and indigenous employment. We have engaged with a recruitment organisation dedicated to assisting members of the community with various disabilities who wanting to enter the workforce. This will be an ongoing activity. As an organisation we have not really made an impact in attracting diversity and are constantly looking at strategies in this area of attraction. | Previosly the Authority did not have any systems or tools or available resources to develop sourcing strategies to help build our talent pool, let alone a diverse talent pool. Building a diverse talent pool in regional areas that are not trasnient ie VISA Holders, travelling workes plus other challenges such as accoomodation, income make building a talent pool difficult and thus stretch our creativity to achieve this target. | 2022 | Human Resources Coordinator | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1 to Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 3; Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5 to Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Annual pay gap reporting | Ongoing | This stategy was implemented in July 2022. The Authority's progress is being made on two fronts. 1) reporting capability/system improvements and 2) procurement of a new payroll system which is planned for implementation in late 2023.Although the measure is implemented noting reporting accuracy and improvements to be made as we transition into a new HR/Payroll system. | Background: Prior to the Authority our organisation had less than 100 employees and had'nt conducted any annual pay gap reporting. Since the Authority's inception in December 2022 our workforce had grown significantly and in 2021/2022 the Authority reported a 7% gender pay gap. Noting the average Australia Gender Pay Gap is 13%. Progress update: during the 2022/2023 reporting period the Authoirty reported a 8% Pay Gap between females and Males noting female salaryies the lesser. An additional barrier was the perception and real life experience of negotiating roles to part time but still having to deliver full time outcomes. This is a common experience for part time staff across organisations and is the contributor to a hidden gender pay gap. Recommendation: With an improved HRIS/Payroll system being implemented we willUndertake organisation-wide, by-level and like-for-like pay gap analyses at least annually. | 2022 | Human Resources Coordinator | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 3
Introduction of fact sheets around flexible working for employees and managers | Complete | This strategy was implemented in August 2022. With the assistance of the Fair Work Commission flexible work best practice guides and regular information sessions run internally for all staff and discussions with staff experiencing workload or mental health issues solutions to support staff were easily accessible. In preperation of the introduction of fact sheets and information sessions we ensured language used was gender neutral and accessible to all staff. | Background: In 2021 Men were less likely to believe there was equal support for those with caring responsibilities regardless of gender (71% compared with 80% of women). This belief was explored in focus groups sessions conducted and we found that men working outdoors in particular could benefit from increased access to flexible working for caring purposes. Only 60% of women agreed with the statement “There is a positive culture within my organisation in relation to employees who use flexible work arrangements” (75% men). The focus groups identified some limitations with part-time work and the impact this was having on career progression. Interventions: The People and Culture team run quartley information sessions for all staff and forms part of an employees onboarding process. Intially the Executive team,we provided resources from FWC to assist in demonstrating available options to manage workload, overtime etc. The Authority's enterprise agreement and policies support various types of flexible work arrangements. We also provided a template to make it easier for the employee to make their request. Also, what ever the type of request, it would be best practice for HR to oversee the request and response before committing to ensure we are compliant and that a copy is provided to HR for the employees records. Impact: Data collected for the 2022/2023 reporting period indicated in increase in flexible work arrangements particularly with working from home where with the exception of our outdoor staff have been provided this arrangement with 45 staff making a formal request. | 2022 | People & Culture Manager | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Education program for all employees on creating positive exible working environments | Ongoing | This stragtey is an ongoing activitiy as we continue to educate staff in their induction, genergal HR knowledge and Wellbeing information sessions throughout the year. | In 2022 the Authority had introduced a Consultative Committee for Change, communicastion and education regarding policies and processes and workplace updates. The review of the Authority's policies, practices and general workplace updates are regularly conducted to ensure they are inclusive and provide equal access to flexible work envrinoment ensuring a positive appraoch was taken.Although the 2022 People Matters Survey focusded on measuring Wellbeing the report/findings presented in August 2022 indicated 78% of staff were confident their request for flexibility would be given due consideration, 8% felt their request wouldnt be given due consideration and 14% were not sure if their request would be duely considered. This indicates further work is required in educating staff around options and process and what flexible work arrangements options can be considered in order to feel confident in their request. | 2023 | People & Culture Team | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Create more inclusive meeting through business rules and best practice | Not started | Due to high workloads and various comittees being established resourcing a working group to adress creating more inclusive meetings has not been started. | Worksrescheduled for second quarter 2024 with a completion date December 2024. | 2023 | People & Culture Team | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Hold a forum for casual and part-time employees to seek their perspectives on diversity and inclusion with particular focus on gender equity | Complete | This strategy was completed in noting further actions to be adressed as a result of the forums held. Through the engagement of an external consultant we were able to eun workshops with our casual and part time staff. | Background: During the initial consultation to inform the Gender Equity Action Plan, there was zero casual or part-time staff representation. Therefore, forums had been arranged to address that issue, and hear from casuals and part-timers. The project was vital that all our staff have a voice in remedying issues such as Gender Equality. Findings: Participants in the focus groups represented a variety of part time and flexible working arrangements. Almost all participants believed that flexible working practices at the Authority were at best practice standards. The flexibility modeled by leaders of all genders around child caring responsibilities was a particular highlight as they saw this gave them permission to do the same. Also, many participants indicated that it had been up to them to ask for flexible working arrangements. This can mean that people struggle without the arrangements they need as they may be concerned that asking will negatively impact them. It can also mean that people who aren't traditionally viewed as flexible work candidates are less likely to access flexibility, i.e. men as carers, people with disability etc. Having managers ask all new employees what flexible working arrangements they require establishes flexibility as the norm. A step further is ensuring that managers also always ask soon to be parents of all genders what leave they will be taking. Another barrier that participants experienced to their career progression was the lack of meaningful promotion opportunities advertised as part time ongoing. Areas for Improvement: Encourage and educate managers to initiate flexible working conversations with all new employees. Advertise all roles as flexible with job share opportunities available. Develop sessions for staff with a focus on casual and part timeers around knowledge of cultural inclusion. | 2023 | Learning & Organisation Development Coordinator | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1; Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4 to Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Review of the parental leave policy | In progress | The Authority's Parental Leave policy is embedded in the organusations 2021-2025 Enterprise agreement. Where there have been enhancements to the policy the organisation has without dissadvantage to the employee. The delay in achieving this objective has primarliy been to resource availability and cost. | Background: The Authority'sd parental leave policy is embedded in its 2021-2025 Enterprise Agreement. The enterprise agreement is read in conjunction with relevant awards and inline with updates from Fair Work. Progress: it is proposed that a policy be created to further enhance those conditions in the enterprise agreement andwill keep up to date with Fair Work changes but also ensure it is a more inclusive document. Furthermore it is proposed the organisation run quarterly information sessions to all staff regarding benefits and access to parental leave provisions. Next Steps: identify resourcing to create a policy ensuring consultation and that the prolcy/process is inclusive and easily interpreted. | 2023 | Human Resources Coordinator | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1; Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5 to Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Develop a set of values and behavioural expectations | In progress | In 2021 when establish our GEAP only 64% of women believed that the organisation encourages respectful workplace behaviours and only 44% believed the Authority took steps to eliminate harassment and discrimination. In the focus groups participants indicated there was concern that when poor behaviours were exhibited appropriate action wasn’t taken. Focus group participants believed that if the organisation had a strong set of values and behavioural expectations that all employees and leaders were held accountable to then there would be a higher level of trust and engagement in the workplace. | Progress: Between July 2022 and June 2023 the Authority had developed in consultation with employees,leadership team and the baord. The values finally adopted: Collaboration, Trust, Leadership and Evidence. This is the essence of who we are. Our Board and staff collaborated to form our Vision and Values statement – this reflects our core principles and ethics and guides the work we do and how we do it. Next Steps: It is planned for early 2024 for the executive team to revisit the values and workshop/consult with the all staff behaviours that will provide futher guidance and application of the organisations values. | 2022 | People & Culture Manager and leadership team | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1 to Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Inclusive Leadership Training | Not started | At the time of developing our GEAP the Authority were in the midst of recruiting a Learning and Organisation Development officer to drive the organisations training program. Due to the organisation not previously having this role in its structure and since the organisations startup as an Authority in December 2021 compliance training took precendence. In late 2022 early 2023 the organisation devepoled and approved an inhouse leadership program which inlcuded Ínclusive Leadership'. The delay has also been in sourcing an apprirate facilitator to deliver the program which has been scheduled for early 2024. | the Authority recognises that there are actions we need to take to lift the behavioural standard of our workplace and to create a safe, supportive, and welcoming environment to all our employees. Starting with our leaders, this Inclusive Leadership Training Program will be delivered in line with our Leadership Program Framework (Me, We, Us), and through the lens of how you will BE as an inclusive leader. You will be encouraged to consider the impact that identity has on work and career; you will be encouraged to create a psychologically safe environment; you will learn about conscious and unconscious bias; you will learn about how to mitigate the impact of bias through system and process change; you will be empowered to become active bystanders and allies; and you will leave more empowered and confident to lead our diverse and inclusive culture. | 2023 | Learning and Organisation Developemnt Cordinator | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1 to Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
Introduce Active Bystander Training | Not started | This programs has yet to actioned due workload and programing conflict issues competing for implementation. | No evaluation or employee training undertaken during the 2022-2023 reporting period due to workload and resource availability and competing time to attend training. It is expected that 40% of employees will have have undertaken Active Bystander Training by August 2024. | 2024 | Learning and Organisation Development Coordinator | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Introduce a person-centred sexual harassment policy | Complete | The Great Ocean Road Coast and Parks Authority has a adopted a Person-led approach whereby the individual impacted chooses how they wish to report it and is involved in the decision about how to handle the issue. It respects the wishes and best interests of the person impacted, but does not mean they solely decide the organisation's response or consequences for the offender because the organisation still owes a duty of care to others. A person-centred approach also recognises that people will share their experience when they feel comfortable and that it may take people time to process what has happened and feel ready to talk. An overly restrictive time limitation between the incident and the report can be a barrier to people speaking up. | Background: In our 2021/2022 People Matters Survey it was reported that 4% (4% improvement on the PMS 2021 results) of employees within the Authority reported experiencing sexual harassment over the last 12 months. Action taken: The Consultative Committee review in consultation with staff and management the existing polcy and reported back some improrovements particularly around clarity, communication and education on having person centered mpolicies particulary around sexual harassment, victimisation, bullying etc. Once the policy was finalised we engaged with an exteral organisation to run training sessions for all leaders and employees across the business. These sessions were mandatory. It was also planned tat the policy would be reviewed annually or upon any legislative changes. Also with the development of a new learning management system, the the sexual harassment policy will be easily accessed by all. Outcome: Although outside of this reportable period we expect to see an improvement in indivuals are made to feel safe and listened too without feeling victimised. | 2023 | People & Culture Manager and Consultative Committee | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Introduce Harassment and Discrimination Contact Ocers (HDCOs) | Not started | This action has yet to commence due to resource availability and competition with other prgrams. Whilist the Authority has Contact Officers on its respective to do list we placed an emphasis of Mental Health Awaremenss training, Health and Safety Represtive (HSR) Training and the establishment of a policy need to be established in the first instance. | It is expected that the Authority will have 10 Harassment and Discrimmination Contact Officers trained by December 2024. | 2024 | Organisation Development and Learning Coordinator | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1: Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
Although the GEAP action items have been asigned to respective indivuals resourcing in part to deliver on these actions has proven to be quite challening as its been in addition to existing workloads. Also, although the Authority identified early on that in adition to people resoucing we had no automated or update systems to capture data in a secure manner nor met privacy or security requirements in the stogae of data. During the 2022-2023 reporting period our organisation need to seek approvals to investing in system upgrades which had not been considered in the GEAP action plan resourcing section. In terms of human rources allocated to the various GEAP actions they were from the People and Culture team allocated to the Learning and Organisation Development Coordinator, Human Resources Coordinator and People and Culture Manager. This was a 3.0 FTE allocation. Upon review and considering budget allocation for a self funded organisation resourcing has been quite challenging particularly when in addition to already heavy workloads. To adress the resourcing issue it is proposed that a working party will be established to share accountabilities from the GEAP action plan in addition to seeking additional budget funding for both external and internal assistance. Please note that this does not diminish our responsiblities and genuine willingness to create an equitable and safe workplace.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | Our workforce has a relatively even balance between men and women, however gender segregation is a concern. Some roles, such as Foreshore Rangers, are mostly held by men whereas office and cleaning roles are mostly held by women. For leadership roles, the three most senior positions in the organisation are held by men however there is gender parity at the manager, coordinator and team leader levels. There have been some recent appointments that have increased the cultural diversity of our team, but according to the People matter survey we have low representation of people with disability, people from non-western backgrounds and LGBTIQA+ people. Our Executive leadership team comprises 4 women and 2 men. Having a gender balanced leadership team is a positive but to create sustainability around this and also to ensure diversity of leadership goes beyond gender, work must be done to make these leadership roles appear more attractive for someone who needs to work in a part-time or flexible capacity. Parents, mostly women and gender diverse folks often experience a time penalty. This means it takes them longer to reach leadership roles and therefore don't spend as much time in them prior to retirement. This means the gap in superannuation and wealth continues to expand. Rethinking leadership roles, providing job share opportunities and supporting part time staff to maintain secure employment whilst seeking promotion are all ways we can reverse this trend. There were comments that leaders who were part-time appeared overstretched and this was negatively impacting their accessibility and perceived performance. | No | No | No | No | Yes | No | No | Operational Priorities: Gender composition at the Authority overall is 50/50. However when broken down we are still male dominated in infrstructure and Planning positions, 90% women in Communications, cleaning/housekeeping positions and 80% of women representing Corporate services in human resource roles and finace roles making up the majority of women.Our environmental teams are represented with a 50% split of men and women filling these positions.
Gender composition of governing bodies | No | The authority had no mechanism to capture/record gender composition of the governing body by Aboriginal and/or Torres Strait Islander identity, age, cultural identity, disability, religion or sexual orientation as at the end of the audit reporting period. | No | No | No | No | No | No | Yes | Having noted this lack of capability the Authority began a process of embarking a system review which had not been completed for this reporting period.
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | All positions have been graded in accordance with the Authority's enterprise agreement classification structure. Each position is grade irrespective and independent to gender. With lack of appropeiate systems in place at the time of the 2022/2023 reporting period extraction of data beyond gender has been challenging . For example conducting alanysis on gender versus position was unattianble. | No | No | No | No | No | No | Yes | Genuine attempt: our organisation is making every effort to genuinely attempt to implement strategies/actions against this indicator and measurable progress arising from the our workforce data. During the 2022/2023 period our organisation was in progress to procure a dedicated human resource information system including remiuneration module and data analysis/reporting ability.
Sexual harassment in the workplace | Yes | The 2022 People Matters survey results indicated 4% of employees had experience sexual harassment in the workplace. This was a 3% improvement of the 2021 results where 7% of staff experience sexual harssment in the workplace. In March 2023 the Authority had undergone a review of its Workplace Deiscrimination, Bullying and Harssment policy with the objective to ensure language used was gender neutral, the policy covers positive prevention and response to sexual harassment matters empowering all staff to act and report innappropriate behaviours. Along side the policy we have developed and delivered face to face training backed by the delopement of online learning. The amend policy also underwent consultation with all staff with executive approval in June 2023. Data: for this reporting period the Authority had Zero sexual harassment complaints recorded. | No | No | No | No | No | Yes | Yes | Genuine attempt: Our organisation makes every attempt to esnure our policies and practices are not only current in compliance but also compliant in access an. In this case we have ensured that the complainant/victim is heard without doubt and that all issued raised begin by taking matters seriously and investigated accordingly.
Recruitment and promotion practices in the workplace | Yes | The 2021 People matter survey reported only 43% of employees believed there was fair and equal recruitment practices. In the focus groups, people believed that there was a history of direct appointments as opposed to advertising positions and undertaking fair recruitment. Although this is believed to have shifted, the focus group participants still felt that unconscious bias and gender stereotypes were influencing recruitment decisions. This section addresses the gender composition at all levels of the workforce, gender pay equity, gendered work segregation and recruitment, and promotion. In 2022 the People Matter Survey results indicated that | No | No | No | Yes | No | Yes | Yes | Genuine attempt and Resourcing: our organisation continues to make genuine attempts to implement this stagety however in addition to day to day operations it’s a start stop effort to research, consult and introduce change. This also has an impact when it comes to prascticality and cost due to resourcing. One of the biggest barriers that participants experienced to their career progression was the lack of meaningful promotion opportunities advertised as part time ongoing. Job security was touted as a strong reason for not applying for promotion as many of the roles were fixed term. Another reason was the need to still work part time.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | Flexible work arrangements although part of the National Employment Statndards is also included in the Great Ocean Road Coast and Parks Authority 2021-2025 Enterprise Agreement. The People & Culture team annually conduct a roadshow to all leaders educating them on Flexible workarrangements educating what it means to give employees meaningful level of control over when, where and how work is accomplished. Throug regular promotion of policies, enterprise agreement and employee assistance program Family violence leave: during the reporting period the Authority had not recieved any requests for access to Family Violence leave. We had xx requests for flexible work arrangements and for those staff who requested working arrangements to support them with family or caring responsibilities we had 44 requests. A significant impact has been educating our executive and senior leadership team to incorprate better questions or advise employees if flexibility was not raised to make it an offering that may assist the employee. | No | No | No | No | No | No | Yes | Genuine attempt: All flexible work arrangements are assessed on a case by case basis with a genuine attempt to cater for each request We believ all efforts are genuine in implmenting related flexible work strategies and reviwed annually against business needs. Also, there are recognised barriers in the workplace for people with child caring responsibilities. It is important that we provide space for people to request flexibility for other reasons as well.
Gendered segregation within the workplace | No | At the time of this reporting period gendered workplace segregation in the workplace was still to be fully understood and explored in our organisation. For the 2022/2023 reporting year the Great Ocean Road Coast and Parks Authority had a total workforceheadcount of 196 or 160.21 FTE. Headcount for women was 106 and men 90. No employee recorded themselves as self described or other. Our executive leadership team of which there are 6 positions comprises 4 women and 2 men. This came from a base of executive team of 2 in 2020/201 where there were 3 executive positions comprising 2 men and 1 vacant. Furthermore for the 2022/2023 reporting period our workforce was stilled skewed towards traditional gendered positions ie Infrastructure and planing consisted 95% males and 5% women, cleaners and housekeepers 75% female and 25% male, corporate services 75% female and 25%male. | No | No | No | No | No | No | No
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled